## Launch Tracker
AI OS for Revenue — Launch Tracker & Task Management
Task ID | Phase | Initiative | Task | Owner | Team | Depends On | Start | Target | Status | Notes
P1-001 | Phase 1 | Init 6 | Design agent skills and prompt templates | Adrien | AI Team | — | 2026-04-27 | 2026-05-07 | NOT STARTED
P1-002 | Phase 1 | Init 6 | Build Slack Block Kit delivery surface | Olga | AI Team | — | 2026-04-27 | 2026-05-11 | NOT STARTED
P1-003 | Phase 1 | Init 6 | Manual simulation: 3 real account queries | Adrien | AI Team | — | 2026-04-30 | 2026-05-07 | NOT STARTED
P1-004 | Phase 1 | Init 6 | Connect HubSpot/Salesforce MCP | Adrien | AI Team | — | 2026-05-04 | 2026-05-22 | NOT STARTED
P1-005 | Phase 1 | Init 6 | Scope Tableau MCP with Bill | Bill | Data Team | — | 2026-05-11 | 2026-06-01 | NOT STARTED
P1-006 | Phase 1 | Init 6 | Provision Slack app + API credentials | Platform | Platform/IT | — | 2026-04-27 | 2026-05-11 | NOT STARTED
P1-007 | Phase 1 | Init 6 | Pilot Concierge with Tom & Leonie | Adrien | AI Team | P1-004 | 2026-05-22 | 2026-06-08 | NOT STARTED
P1-008 | Phase 1 | Init 6 | Define outcome framework and evaluation criteria | Olga | AI Team | — | 2026-05-04 | 2026-05-18 | NOT STARTED
P1-101 | Phase 1 | Init 1 | Define Salesforce trigger for new opportunities | Adrien | AI Team | — | 2026-04-27 | 2026-05-04 | NOT STARTED
P1-102 | Phase 1 | Init 1 | Map account plan output to team template | Olga | AI Team | — | 2026-04-30 | 2026-05-11 | NOT STARTED
P1-103 | Phase 1 | Init 1 | Build enrichment pipeline (context, stakeholders) | Adrien | AI Team | P1-101 | 2026-05-04 | 2026-05-18 | NOT STARTED
P1-104 | Phase 1 | Init 1 | Manual simulation: 3 real account plans | Adrien | AI Team | P1-102 | 2026-05-11 | 2026-05-18 | NOT STARTED
P1-105 | Phase 1 | Init 1 | Co-build round 1 with ADs | Brett | Sales | P1-104 | 2026-05-18 | 2026-05-25 | NOT STARTED
P1-106 | Phase 1 | Init 1 | Co-build round 2: refine output | Adrien | AI Team | P1-105 | 2026-05-25 | 2026-06-01 | NOT STARTED
P1-107 | Phase 1 | Init 1 | Co-build round 3: final iteration | Olga | AI Team | P1-106 | 2026-06-01 | 2026-06-08 | NOT STARTED
P1-108 | Phase 1 | Init 1 | Define MEDDPICC field mappings with RevOps | RevOps | RevOps | — | 2026-05-11 | 2026-05-25 | NOT STARTED
P2-001 | Phase 2 | Init 3 | Build narrative critic agent | Adrien | AI Team | P1-004 | 2026-06-08 | 2026-06-22 | NOT STARTED
P2-002 | Phase 2 | Init 3 | Build stakeholder mapper | Olga | AI Team | P1-004 | 2026-06-08 | 2026-06-22 | NOT STARTED
P2-003 | Phase 2 | Init 3 | Design strategic soundboard interaction | Adrien | AI Team | P2-001 | 2026-06-15 | 2026-06-29 | NOT STARTED
P2-004 | Phase 2 | Init 3 | Integrate Tableau performance data | Bill | Data Team | P1-005 | 2026-06-15 | 2026-06-29 | NOT STARTED
P2-005 | Phase 2 | Init 3 | Test with AD team: 3 sample narratives | Tom | Sales | P2-003 | 2026-06-29 | 2026-07-13 | NOT STARTED
P2-006 | Phase 2 | Init 3 | Refine based on AD feedback | Adrien | AI Team | P2-005 | 2026-07-13 | 2026-07-27 | NOT STARTED
P2-007 | Phase 2 | Init 3 | QBR template integration testing | Tom | Sales | P2-006 | 2026-07-20 | 2026-08-03 | NOT STARTED
P2-101 | Phase 2 | Init 4 | Decide transcript vendor (Gong vs Fireflies) | Tom | Leadership | — | 2026-04-27 | 2026-05-11 | NOT STARTED
P2-102 | Phase 2 | Init 4 | Build transcript ingestion pipeline | Data Team | Data Team | P2-101 | 2026-05-25 | 2026-06-22 | NOT STARTED
P2-103 | Phase 2 | Init 4 | Build theme summarisation agent | Olga | AI Team | P2-102 | 2026-06-22 | 2026-07-06 | NOT STARTED
P2-104 | Phase 2 | Init 4 | Define churn signal taxonomy with Sarah | Sarah | CSM | — | 2026-06-08 | 2026-06-22 | NOT STARTED
P2-105 | Phase 2 | Init 4 | Build escalation drafter | Adrien | AI Team | P2-103 | 2026-06-29 | 2026-07-13 | NOT STARTED
P2-106 | Phase 2 | Init 4 | Back-test against historical churn cases | Adrien | AI Team | P2-105 | 2026-07-13 | 2026-07-27 | NOT STARTED
P2-107 | Phase 2 | Init 4 | CSM pilot: 3-week trial with Sarah's team | Sarah | CSM | P2-106 | 2026-07-27 | 2026-08-17 | NOT STARTED
P3-001 | Phase 3 | Init 5 | Build objection digest agent | Olga | AI Team | P2-102 | 2026-07-20 | 2026-08-03 | NOT STARTED
P3-002 | Phase 3 | Init 5 | Build pipeline inspection workflow | Adrien | AI Team | P3-001 | 2026-07-27 | 2026-08-10 | NOT STARTED
P3-003 | Phase 3 | Init 5 | Coaching theme detection across reps | Olga | AI Team | P3-001 | 2026-07-27 | 2026-08-10 | NOT STARTED
P3-004 | Phase 3 | Init 5 | Leadership pilot: 2-week trial | James | Leadership | P3-002 | 2026-08-10 | 2026-08-24 | NOT STARTED
P3-005 | Phase 3 | Init 5 | Refine based on leadership feedback | Adrien | AI Team | P3-004 | 2026-08-24 | 2026-09-07 | NOT STARTED
P4-001 | Phase 4 | Init 2 | Name Ops counterpart and scope data access | TBC | Ops | — | TBD | TBD | DEFERRED
P4-002 | Phase 4 | Init 2 | Document Snowflake schema for revenue tables | TBC | Data Team | P4-001 | TBD | TBD | DEFERRED
P4-003 | Phase 4 | Init 2 | Define expansion business rules with Ops | TBC | Ops | P4-001 | TBD | TBD | DEFERRED
P4-004 | Phase 4 | Init 2 | Build expansion validator prototype | Adrien | AI Team | P4-002 | TBD | TBD | DEFERRED
P4-005 | Phase 4 | Init 2 | Build margin risk flagger | Olga | AI Team | P4-003 | TBD | TBD | DEFERRED

## Dependencies
Cross-Initiative Data Dependencies
Initiative | HubSpot/SF | Tableau | Snowflake | Transcripts | Service Tickets | Dependency Count
6. Data Concierge | REQUIRED | REQUIRED | REQUIRED | REQUIRED | REQUIRED | 5
1. New Business Execution | REQUIRED | — | — | REQUIRED | — | 2
3. AD Strategic Narrative | REQUIRED | REQUIRED | — | REQUIRED | — | 3
4. CSM Retention Guardian | REQUIRED | — | REQUIRED | REQUIRED | REQUIRED | 4
5. Leadership Synthesis | REQUIRED | REQUIRED | REQUIRED | REQUIRED | — | 4
2. Growth AE Expansion | REQUIRED | REQUIRED | REQUIRED | — | — | 3

## Connectors
Data Connector Status & Ownership
Connector | Risk Level | Owner | Timeline | Status | Unlocks | Blockers
HubSpot / Salesforce | LOW | Adrien / Olga | Wk 2–5 | NOT STARTED | Init 6 (CRM queries), Init 1 (pre-call briefs), Init 3 (account context) | Platform: API keys needed
Tableau | MEDIUM | Bill | Wk 3–7 | NOT STARTED | Init 6 (fulfillment data), Init 3 (performance proof), Init 5 (pattern data) | Version compatibility unknown
Transcripts | MEDIUM | Tom (decide vendor) | Wk 5–9 | BLOCKED | Init 1 (post-call), Init 4 (theme synthesis), Init 5 (objection digest) | Vendor not chosen, DPIA may be needed
Snowflake | HIGH | TBC — BLOCKER | Wk 7–13 | BLOCKED | Init 6 (deep analytics), Init 2 (expansion economics), Init 4 (service data) | No named owner, schema undocumented
Service Tickets | HIGH | TBC — BLOCKER | Wk 8–13 | BLOCKED | Init 4 (service themes), Init 6 (proactive alerts) | System unknown (Zendesk/Jira/HubSpot?)

## Team RACI
Team RACI Matrix — Who Does What
Activity | AI Team | Data Team | RevOps | Data Science | Platform/IT
Agent skill design & prompt engineering | R/A | — | C | — | —
Slack surface design & delivery | R/A | — | — | — | C
MCP server builds (HubSpot, Tableau, Snowflake) | C | R/A | — | — | C
Transcript ingestion pipeline | C | R/A | — | — | —
Metric definitions & KPI dimensions | C | — | R/A | — | —
Data accuracy & quality | I | C | R/A | — | —
Churn prediction model (ML) | C | — | — | R/A | —
Forecast confidence model (ML) | C | — | — | R/A | —
API credentials & tool provisioning | C | — | — | — | R/A
Slack app provisioning | C | — | — | — | R/A
Pilot user feedback collection | R/A | — | C | — | —
Output format validation | R | — | A | — | —
Workflow orchestration logic | R/A | — | — | — | —
Schema documentation | I | R/A | — | — | —
Business rule definitions | C | — | R/A | — | —
Legend:
R/A = Responsible & Accountable
R = Responsible
A = Accountable
C = Consulted
I = Informed