## Overview
AI OS for Revenue — Testing & QA Matrix
Test cases, acceptance criteria, and go/no-go gates for all six initiatives
Init # | Initiative | Phase | Total Tests | Pass | Fail | Pending
6 | Revenue Data Concierge | Phase 1 | 8 | 0 | 0 | 14
1 | New Business Execution | Phase 1 | 7 | 0 | 0 | 13
3 | AD Strategic Narrative | Phase 2 | 7 | 0 | 0 | 13
4 | CSM Retention Guardian | Phase 2 | 7 | 0 | 0 | 13
5 | Leadership Synthesis | Phase 3 | 6 | 0 | 0 | 12
2 | Growth AE Expansion | Phase 4 | 5 | 0 | 0 | 11

## Init 6
Initiative 6: Revenue Data Concierge — Test Cases
Phase 1 ¦ Testing & Acceptance Criteria
Test ID | Test Name | Description | Method | Acceptance Criteria | Stage | Owner | Status | Notes
TC-6.01 | HubSpot MCP Connection | MCP server connects to HubSpot and returns account data | Query 5 known accounts, verify data matches HubSpot UI | 100% match | Scope | Adrien | PENDING
TC-6.02 | Natural Language Query | Slack interface interprets NL queries correctly | Test 10 varied query phrasings for same data point | 8/10 correct interpretation | Build | Olga | PENDING
TC-6.03 | Response Latency | Query-to-answer time under 60 seconds | Time 20 queries across different data sources | 95th percentile < 60s | Test | Adrien | PENDING
TC-6.04 | Citation Accuracy | Every response cites its data source | Verify 15 responses include clickable source links | 100% citation rate | Test | Olga | PENDING
TC-6.05 | Tableau Data Access | Tableau MCP returns fulfillment/performance data | Query 5 known metrics, verify against Tableau dashboard | 100% match | Build | Bill | PENDING
TC-6.06 | Pilot User Satisfaction | Tom and Leonie rate experience 4+/5 | 2-week pilot with daily usage, structured feedback form | Average rating >= 4.0 | Pilot | Tom | PENDING
TC-6.07 | Error Handling | System handles bad queries gracefully | Submit 5 ambiguous/impossible queries | No crashes, helpful error messages | Test | Olga | PENDING
TC-6.08 | Adoption Metric Baseline | Track Tableau direct login frequency | Record baseline logins for 2 weeks pre-launch | Baseline established | Scope | Adrien | PENDING
GO / NO-GO CRITERIA
1 | HubSpot MCP returns accurate data for all test queries | [5 empty] | PENDING
2 | Slack NL interface achieves 80%+ correct interpretation | [5 empty] | PENDING
3 | Response latency under 60s at 95th percentile | [5 empty] | PENDING
4 | 100% citation rate on all responses | [5 empty] | PENDING
5 | Pilot users rate 4+/5 average satisfaction | [5 empty] | PENDING
LAUNCH DECISION: | [6 empty] | PENDING

## Init 1
Initiative 1: New Business Execution — Test Cases
Phase 1 ¦ Testing & Acceptance Criteria
Test ID | Test Name | Description | Method | Acceptance Criteria | Stage | Owner | Status | Notes
TC-1.01 | Salesforce Trigger | New opportunity fires workflow | Create 5 test opportunities in Salesforce | 100% trigger rate | Build | Adrien | PENDING
TC-1.02 | Account Plan Format | Output matches existing team template | Compare 3 outputs against template structure | All sections present, correct order | Test | Olga | PENDING
TC-1.03 | Enrichment Accuracy | Stakeholder and touchpoint data is correct | Verify 5 account enrichments against CRM records | 95%+ data accuracy | Test | Adrien | PENDING
TC-1.04 | Discovery Questions | Generated questions are relevant and actionable | ADs rate 10 sets of discovery questions 1-5 | Average >= 4.0 | Pilot | Brett | PENDING
TC-1.05 | Positioning Angles | Objection handling is relevant to account context | 3 ADs review positioning for their real accounts | Approved by 3/3 ADs | Pilot | Leonie | PENDING
TC-1.06 | Post-Call Synthesis | Transcript analysis produces accurate follow-ups | Compare 5 syntheses against manual notes | 90%+ key point capture | Test | Olga | PENDING
TC-1.07 | Co-Build Iteration | AD feedback incorporated across 3 rounds | Track feedback items resolved per round | 80%+ items addressed | Refine | Adrien | PENDING
GO / NO-GO CRITERIA
1 | Salesforce trigger fires 100% on new opportunities | [5 empty] | PENDING
2 | Account plan output matches team template format | [5 empty] | PENDING
3 | 3 ADs approve output quality | [5 empty] | PENDING
4 | Enrichment data 95%+ accurate | [5 empty] | PENDING
5 | Post-call synthesis captures 90%+ key points | [5 empty] | PENDING
LAUNCH DECISION: | [6 empty] | PENDING

## Init 3
Initiative 3: AD Strategic Narrative — Test Cases
Phase 2 ¦ Testing & Acceptance Criteria
Test ID | Test Name | Description | Method | Acceptance Criteria | Stage | Owner | Status | Notes
TC-3.01 | Narrative Critic Quality | Agent identifies genuine weaknesses in narratives | Submit 5 narratives with known gaps | Identifies 80%+ of planted gaps | Test | Adrien | PENDING
TC-3.02 | Stakeholder Map Accuracy | Generated maps match AD manual versions | Compare 3 maps against AD-built versions | 90%+ stakeholder coverage | Test | Olga | PENDING
TC-3.03 | Strategic Depth | Soundboard interaction goes beyond surface-level | 3 ADs rate Q&A depth 1-5 | Average >= 4.0 | Pilot | Tom | PENDING
TC-3.04 | Tableau Integration | Performance data flows into narrative context | Verify 5 narratives include correct metrics | 100% data accuracy | Build | Bill | PENDING
TC-3.05 | Transcript Context | Conversation intelligence enriches narrative | Compare narrative with/without transcript context | Measurable quality improvement | Test | Olga | PENDING
TC-3.06 | QBR Template Fit | Output integrates with existing QBR format | Run 3 QBR preps using the agent | ADs approve format fit | Pilot | Tom | PENDING
TC-3.07 | C-Suite Readiness | Output quality suitable for executive audience | Leadership reviews 3 sample narratives | Approved for external use | Refine | Tom | PENDING
GO / NO-GO CRITERIA
1 | Narrative critic identifies 80%+ of known gaps | [5 empty] | PENDING
2 | Stakeholder maps 90%+ accurate vs manual | [5 empty] | PENDING
3 | Tableau data flowing correctly | [5 empty] | PENDING
4 | ADs rate strategic depth 4+/5 | [5 empty] | PENDING
5 | Output approved for C-suite audience | [5 empty] | PENDING
LAUNCH DECISION: | [6 empty] | PENDING

## Init 4
Initiative 4: CSM Retention Guardian — Test Cases
Phase 2 ¦ Testing & Acceptance Criteria
Test ID | Test Name | Description | Method | Acceptance Criteria | Stage | Owner | Status | Notes
TC-4.01 | Theme Summarisation | Recurring topics correctly identified across transcripts | Run on 20 transcripts, compare against manual themes | 80%+ theme match | Test | Olga | PENDING
TC-4.02 | Escalation Draft Quality | Auto-generated proposals are accurate and appropriate | CSMs rate 5 drafts for accuracy and tone | Average >= 4.0 | Pilot | Sarah | PENDING
TC-4.03 | False Positive Rate | Healthy accounts not flagged as at-risk | Test against 10 known healthy accounts | Zero false positives | Test | Adrien | PENDING
TC-4.04 | Service Ticket Integration | Ticket themes correctly categorised | Verify 15 ticket theme classifications | 85%+ accuracy | Build | TBC | PENDING
TC-4.05 | Historical Back-Test | System would have caught past churn cases | Run against 10 historical churn events | 80%+ detection rate | Test | Adrien | PENDING
TC-4.06 | Transcript Pipeline | Transcripts ingested and retrievable | Ingest 50 transcripts, query 10 specific conversations | 100% retrieval success | Build | Data Team | PENDING
TC-4.07 | CSM Pilot Approval | CSM team validates utility in daily workflow | 3-week pilot with structured daily feedback | 80%+ daily usage rate | Pilot | Sarah | PENDING
GO / NO-GO CRITERIA
1 | Theme summarisation 80%+ match with manual | [5 empty] | PENDING
2 | Zero false positive churn signals | [5 empty] | PENDING
3 | Back-test catches 80%+ historical churn | [5 empty] | PENDING
4 | CSM team 80%+ daily usage in pilot | [5 empty] | PENDING
5 | Transcript pipeline 100% retrieval | [5 empty] | PENDING
LAUNCH DECISION: | [6 empty] | PENDING

## Init 5
Initiative 5: Leadership Synthesis — Test Cases
Phase 3 ¦ Testing & Acceptance Criteria
Test ID | Test Name | Description | Method | Acceptance Criteria | Stage | Owner | Status | Notes
TC-5.01 | Objection Digest | Common objections match leadership observations | Compare digest against leadership's known patterns | 90%+ pattern match | Test | James | PENDING
TC-5.02 | Pipeline Risk Flags | Risk flags correlate with deal outcomes | Back-test against 20 historical deal outcomes | 75%+ correlation | Test | Adrien | PENDING
TC-5.03 | Coaching Themes | Detected patterns are real, not noise | Leadership validates 10 detected themes | 80%+ validated as real | Pilot | Tom | PENDING
TC-5.04 | Cross-Rep Patterns | Pattern detection works at scale | Run across 5+ reps, verify patterns | Consistent detection across reps | Test | Olga | PENDING
TC-5.05 | Forecast Guardrail | System does NOT produce forecast scores | Verify no confidence scores in 20 outputs | Zero forecast scores present | Test | Adrien | PENDING
TC-5.06 | Leadership Pilot | James, Tom, Leonie approve for weekly use | 2-week pilot with structured feedback | All 3 approve for continued use | Pilot | James | PENDING
GO / NO-GO CRITERIA
1 | Objection digest 90%+ matches leadership observations | [5 empty] | PENDING
2 | Pipeline risk flags 75%+ correlation with outcomes | [5 empty] | PENDING
3 | Zero forecast confidence scores in output | [5 empty] | PENDING
4 | All 3 leaders approve for weekly use | [5 empty] | PENDING
5 | Cross-rep patterns validated across 5+ reps | [5 empty] | PENDING
LAUNCH DECISION: | [6 empty] | PENDING

## Init 2
Initiative 2: Growth AE Expansion — Test Cases
Phase 4 ¦ Testing & Acceptance Criteria
Test ID | Test Name | Description | Method | Acceptance Criteria | Stage | Owner | Status | Notes
TC-2.01 | Snowflake Data Access | Ops economics data is queryable | Query 5 known data points from Snowflake | 100% data retrieval | Scope | TBC | PENDING
TC-2.02 | Business Rule Validation | Expansion logic confirmed by Ops | Ops counterpart reviews 10 business rules | 100% confirmed | Scope | TBC | PENDING
TC-2.03 | Pressure Test Simulation | Profitability validator works on real deals | Run on 3 historical expansion deals | Results match known outcomes | Test | Adrien | PENDING
TC-2.04 | Margin Risk Accuracy | Agency reliance calculations are correct | Verify 5 margin calculations against actuals | 95%+ accuracy | Test | Olga | PENDING
TC-2.05 | Output Format Approval | Growth AE team approves deliverable format | 3 Growth AEs review sample outputs | Approved by 3/3 | Pilot | Leonie | PENDING
GO / NO-GO CRITERIA
1 | Snowflake ops data accessible and schema documented | [5 empty] | PENDING
2 | Ops counterpart confirms 100% of business rules | [5 empty] | PENDING
3 | Pressure test matches known historical outcomes | [5 empty] | PENDING
4 | Margin calculations 95%+ accurate | [5 empty] | PENDING
5 | Growth AE team approves output format | [5 empty] | PENDING
LAUNCH DECISION: | [6 empty] | PENDING