ENGINEERING SPRINT PLAN

AI Operating System for Revenue

Sprint 1: Foundation & Quick Win (Weeks 1–6)

Owner: Adrien Enjalbert (Head of Digital & Applied AI)

Date: April 2026 | Version: 1.0

Audience: Engineering, AI Team, Data Team

# Sprint Overview

Sprint Goal: Deliver the Data Concierge foundation (Init 6) with HubSpot + Salesforce MCP connectors, and ship a working New Business Agent MVP (Init 1) with prospect research + ICP scoring to pilot users.

| Dates | Duration | Team Size | Tracks |
| --- | --- | --- | --- |
| W1 — W6 (May – Jun 2026) | 6 weeks | 3 core + 2 dependent | Track 1 (Foundation) + Track 2 (Quick Win) |

# Team Capacity

Planned at 70% of raw capacity to allow for interrupts, meetings, on-call, and discovery work.

| Person | Role | Available Days | Effective Days | Points | Notes |
| --- | --- | --- | --- | --- | --- |
| Adrien E. | Lead / Architect | 30 / 30 | 21 | 42 | Split: 60% architecture, 40% hands-on |
| Olga | AI Engineer | 30 / 30 | 21 | 42 | Primary builder for agent skills & prompts |
| Data Team (TBD) | Data Eng | 15 / 30 | 10 | 20 | 50% allocation — needs confirmation from Data Lead |
| Bill | Tableau / BI | 5 / 30 | 4 | 8 | Tableau API access only — limited scope |
| Tom | Decision Maker | 2 / 30 | 2 | — | Decision on transcript platform only |
| TOTAL |  | 82 / 150 | 58 | 112 pts | 70% capacity = ~78 planned points |

Risk: Data Team allocation is unconfirmed. If unavailable, Snowflake and Service Ticket connectors slip to Sprint 2. Mitigation: Adrien to escalate by end of W1.

# Sprint Backlog

Items are sequenced by dependency. Track 1 (Init 6 — Data Concierge/Foundation) must deliver the OS core before Track 2 (Init 1 — New Business Agent) can be fully connected.

## Track 1: Foundation — Init 6 (Data Concierge)

Build the shared OS backbone: MCP connector framework, Slack app shell, and the first data connectors.

| Pri | Item | Est | Owner | Week | Dependencies / Notes |
| --- | --- | --- | --- | --- | --- |
| P0 | MCP Server scaffold — connection manager, auth layer, config schema | 8 pts | Adrien | W1–W2 | None. Foundation for all connectors. |
| P0 | HubSpot MCP connector — contacts, companies, deals, activities via API | 5 pts | Adrien | W2–W3 | Blocked by: MCP scaffold. HubSpot API key needed from RevOps. |
| P0 | Salesforce MCP connector — accounts, opportunities, contacts, tasks via API | 5 pts | Adrien | W3–W4 | Blocked by: MCP scaffold. SF connected app + OAuth setup with IT. |
| P0 | Slack App shell — bot user, event subscriptions, Block Kit message framework | 5 pts | Olga | W1–W2 | Needs Slack workspace admin approval. Parallel with MCP scaffold. |
| P0 | Agent orchestration layer — skill router, context window manager, memory store | 8 pts | Olga | W2–W4 | Core AI engine. Claude API integration + prompt management. |
| P1 | Tableau MCP connector — read-only dashboard data extraction | 3 pts | Bill | W3–W4 | Bill owns. Needs Tableau Server API access. |
| P1 | Shared data schema — unified account/contact/opportunity model across CRM sources | 5 pts | Adrien | W4–W5 | After HubSpot + SF connectors are working. |
| P2 | Snowflake MCP connector — read access to data warehouse | 5 pts | Data Team | W4–W6 | HIGH RISK: No owner confirmed. Needs Data Lead assignment. |
| P2 | Service Ticket connector — support case data for CSM intelligence | 5 pts | Data Team | W5–W6 | HIGH RISK: No owner confirmed. Depends on Snowflake connector. |

Track 1 Total: 49 points | P0 = 31 pts, P1 = 8 pts, P2 = 10 pts

## Track 2: Quick Win — Init 1 (New Business Agent)

First user-facing agent. Delivers prospect research, ICP scoring, and pre-call briefs to Slack for pilot users (Leonie, Brett).

| Pri | Item | Est | Owner | Week | Dependencies / Notes |
| --- | --- | --- | --- | --- | --- |
| P0 | New Business agent skill — prospect research prompt chain + ICP scoring logic | 8 pts | Olga | W3–W5 | Blocked by: Agent orchestration layer (Track 1). |
| P0 | CRM data enrichment pipeline — pull HubSpot deal data, enrich with web research | 5 pts | Adrien | W4–W5 | Blocked by: HubSpot connector (Track 1). |
| P0 | Slack delivery surface — Block Kit templates for prospect cards, briefs, action buttons | 5 pts | Olga | W4–W5 | Blocked by: Slack App shell (Track 1). |
| P1 | Pilot onboarding — Leonie + Brett setup, feedback loop, usage tracking | 3 pts | Adrien | W5–W6 | Needs working agent + Slack delivery. |
| P1 | Pre-call brief template — automated daily Slack brief for upcoming meetings | 3 pts | Olga | W5–W6 | Stretch if agent skill takes longer. Calendar API integration. |

Track 2 Total: 24 points | P0 = 18 pts, P1 = 6 pts

Sprint Load: 73 points (P0+P1) of 78 planned capacity = 94% utilisation. P2 items (10 pts) are stretch goals that require Data Team availability. If Data Team is unavailable, sprint load drops to 63 points (81%) — a healthy buffer.

# Technical Architecture

## System Components

The AI OS follows a four-layer architecture. Sprint 1 focuses on establishing layers 1–3.

| Layer | Components (Sprint 1) | Owner | Status |
| --- | --- | --- | --- |
| L1: Platform / Tools | Slack App, Block Kit, OAuth tokens | Olga | Build in W1–W2 |
| L2: Data Connectors | MCP Server, HubSpot, Salesforce, Tableau connectors | Adrien + Bill | Build in W1–W4 |
| L3: AI Intelligence | Agent orchestrator, skill router, prompt chains, memory | Olga + Adrien | Build in W2–W5 |
| L4: Business Logic | ICP scoring, prospect research, pre-call brief generation | Olga | Build in W3–W6 |

## MCP Connector Specification

Each MCP connector follows a standard interface:

- Auth: OAuth2 for Salesforce, API key for HubSpot, Personal Access Token for Tableau

- Schema: JSON schema definition per connector with typed fields and relationships

- Operations: read (query), list (paginated), search (filtered), aggregate (counts/sums)

- Rate limiting: Per-connector throttle with exponential backoff (HubSpot: 100/10s, SF: 15k/day)

- Error handling: Retry with backoff, graceful degradation, structured error responses to agent

- Caching: TTL-based cache per entity type (contacts: 5min, deals: 1min, activities: real-time)

## Agent Skill Architecture

New Business Agent (Init 1) skill chain:

- 1. Trigger: Slack command or scheduled cron (daily pre-call)

- 2. Context Assembly: Pull prospect data from HubSpot + Salesforce via MCP connectors

- 3. Web Research: Enrich with company news, LinkedIn data, recent funding

- 4. ICP Scoring: Score prospect against ideal customer profile criteria (industry, size, tech stack, intent signals)

- 5. Brief Generation: Claude prompt chain produces structured brief with talking points

- 6. Delivery: Block Kit message to Slack with action buttons (schedule call, add to sequence, flag for review)

# Risks & Mitigations

| Risk | ROAM | Impact | Mitigation | Owner / Deadline |
| --- | --- | --- | --- | --- |
| Data Team allocation unconfirmed — Snowflake + Service Ticket connectors blocked | OWNED | HIGH | Escalate to Data Lead by W1. If no allocation, defer P2 items to Sprint 2. | Adrien — End of W1 |
| Salesforce OAuth setup requires IT involvement — potential 2-week lead time | OWNED | MEDIUM | Submit connected app request immediately. Use sandbox credentials for dev. | Adrien — W1 Day 1 |
| Slack workspace admin approval may be slow | OWNED | MEDIUM | Pre-submit app manifest. Develop with test workspace in parallel. | Olga — W1 Day 1 |
| Claude API rate limits may constrain agent throughput at scale | ACCEPTED | LOW | Not a Sprint 1 concern — pilot is 2 users. Monitor and plan for Sprint 3. | Adrien — Sprint 3 |
| Transcript platform decision pending (Tom) — blocks Init 3 prep | OWNED | MEDIUM | Not blocking Sprint 1 directly, but decision needed by Sprint 2 start. | Tom — End of W6 |

# Definition of Done

## Per Item

- Code reviewed and merged to main branch

- Unit tests passing with >80% coverage on new code

- Integration tests for each MCP connector (auth, CRUD, error handling)

- Documentation updated (README, API spec, connector config guide)

- Tested in staging environment with real credentials

- Slack message templates validated with Block Kit Builder

- Product sign-off from Adrien on output quality

## Sprint Done Criteria

- MCP Server running with HubSpot + Salesforce connectors pulling live data

- Slack App installed in workspace, responding to commands

- New Business Agent producing prospect briefs from real CRM data

- Pilot users (Leonie, Brett) have received at least 1 agent-generated brief

- Feedback loop established: pilot users can rate and comment on brief quality

- All P0 items shipped. P1 items shipped or explicitly deferred with rationale.

# Key Dates

| Date | Event | Attendees | Purpose |
| --- | --- | --- | --- |
| W1 Day 1 | Sprint Kickoff | Adrien, Olga, Data Team | Align on goals, assign items, confirm capacity |
| W1 Day 1 | IT / Admin Requests Submitted | Adrien, Olga | SF connected app, Slack app approval, API keys |
| W2 End | Checkpoint: MCP Scaffold + Slack Shell | Adrien, Olga | Verify foundation layers are working |
| W3 End | Mid-Sprint Review | Full team | Demo connectors, assess Track 2 readiness |
| W5 Start | Pilot User Onboarding | Adrien, Leonie, Brett | Setup Slack channels, demo agent, collect first feedback |
| W6 End | Sprint Demo & Retro | Full team + stakeholders | Demo working system, collect feedback, plan Sprint 2 |
| W6 End | Sprint 2 Planning | Adrien, Olga | Scope Init 3 (AD Narrative) + carry-over items |

# Sprint 2 Preview

Sprint 2 (W7–W12) will focus on Init 3 (AD Narrative Engine) as the primary track, with Init 6 connector expansion as the secondary track.

- Primary: Init 3 — AD Narrative Engine: transcript ingestion, meeting summary agent, narrative generation for leadership

- Secondary: Init 6 expansion — Snowflake connector (if deferred), transcript connector (pending Tom’s decision)

- Carry-over: Any P1/P2 items not shipped in Sprint 1

- Dependency: Tom’s transcript platform decision must land by Sprint 1 end to unblock Init 3 planning