AI OPERATING SYSTEM FOR REVENUE

SLT Executive Brief

Adrien  |  Head of Digital & Applied AI  |  April 2026

| YELLOW | At Risk: AI intelligence layer is ready to ship. Foundation data connectors need Data Team commitment to unblock 4 of 6 initiatives. Two tracks can start immediately. |
| --- | --- |

# TL;DR

We have designed an AI Operating System that replaces six separate AI projects with one system and six surfaces. The AI layer (skills, agents, Slack delivery) is built and ready. Two tracks can start this week: Init 6 (Data Concierge, HubSpot-only) and Init 1 (New Business account plans). The remaining four initiatives are gated on Data Team connectors, RevOps metric definitions, and Platform credentials. We need three decisions from SLT to proceed.

# Progress Against Goals

- Architecture validated: Four-layer system (AI Intelligence, Data Connector, Business Logic, Platform) designed with clear ownership boundaries. One foundation, six reusable surfaces.

- Launch sequencing defined: 20-week phased roadmap across 4 phases. Two parallel tracks running from Week 1. Each phase compounds the last.

- Pilot users identified: Tom and Leonie for Slack pilot (Init 6), Brett as pilot AE (Init 1). AD co-build confirmed for Init 3.

- Five data connectors mapped: HubSpot/Salesforce (LOW risk, ready), Tableau (MEDIUM, Bill named), Transcripts (MEDIUM, vendor TBD), Snowflake and Service Tickets (HIGH, no owner).

# Initiative Status Overview

| # | Initiative | Status | Key Constraint | Next Milestone |
| --- | --- | --- | --- | --- |
| 6 | Data Concierge | GREEN | HubSpot-only v1 can start now | Slack pilot W3-6 with Tom & Leonie |
| 1 | New Business | GREEN | No blockers for v1 (Salesforce data) | Account plan agent v1 in weeks |
| 3 | AD Narrative | YELLOW | Needs transcripts + Tableau data | Ships after Init 1, 4, 5 prove pipeline |
| 4 | CSM Retention | YELLOW | Blocked on transcript pipeline (Tom) | Theme summarisation W9-12 |
| 5 | Leadership | YELLOW | Blocked on transcripts + RevOps | Objection digest W9-12 |
| 2 | Growth AE | RED | 90% blocked on Ops data, no owner | Deferred to FY26/27 |

# Risks

| Risk | Impact | ROAM | Mitigation |
| --- | --- | --- | --- |
| Snowflake has no named owner | Init 2, 4, 6 (deep) blocked | OWNED needed | SLT to assign Data Team resource by W2 |
| Transcript vendor not decided | Init 1, 4, 5 post-call features blocked | OWNED (Tom) | Tom to decide Gong vs Fireflies by W4 |
| RevOps resource not allocated | AI outputs business-wrong without validation | ACCEPTED | AI team ships; RevOps validates in parallel |
| Churn model needs 12+ months data | Init 4 churn scoring not buildable | ACCEPTED | Ship theme summarisation now; ML deferred to Data Science |

# Decisions Needed from SLT

- Name a Data Team owner for the foundation connectors. Snowflake, service tickets, and transcript pipeline all need a named engineer committed to Week 1 scoping. Without this, agents have nothing to query. Need by: End of next week.

- Approve Track 2 (Init 1) for immediate co-build with ADs. No blockers, high confidence, earns trust fast. Brett confirmed as pilot AE. Need by: This week.

- Agree that Init 2, 4, 5 wait for the foundation. No parallel pilots on blocked initiatives. Three surfaces in 6 months, not six. Need by: Before Sprint 1 kickoff.

# Next Milestones

| Timeline | Milestone | Owner |
| --- | --- | --- |
| W1-2 | Agent skill design + manual simulation with real accounts | AI Team |
| W3-6 | Concierge v1 (HubSpot-only) live in Slack | AI Team + Platform |
| W5-8 | Account plan agent v1 shipping with pilot AEs | AI Team |
| W9-12 | Pre-call briefs + CSM digest + leadership objections in Slack | AI Team + Data |
| W17-20 | Full operating system live across all committed surfaces | All teams |